## Sheet1
Sr. No. | Module | Sub Module |  | Features | Comments |  | January | Fabuary |  |  |  | March
[7 empty] | Week1(25th Jan 2021 to 1st Feb 2021) | Week1(1st Feb 2021 to 5th Feb 2021) | Week2(8th Feb 2021 to 12th Feb 2021) | Week3(15th Feb 2021 to 19th Feb 2021) | Week4(22nd Feb 2021 to 26th Feb 2021) | Week1(1st March 2021 to 5th March 2021) | status
1 | Architecture Diagram |  |  |  |  | Vidhi,Vrunda & Harshil
2 | Technology Stack
3 | Data flow Diagram
4 | Database Design
5 | Frontend Admin Web Application | General | Login |  |  | Vidhi
|  | Provider Management | Service Provider | Manage Provider | Add Provider
Delete Provider
Update Provider
View Provider
|  | Service Management | Services | Manage Services | Add New Services
Update Services
Delete Services
View Services
|  | Order Management | Orders | Manage Orders | View Orders
Confirmed/Reject Order
|  | Feedback Management | Feedback | Manage Feedback | View Feedback
Delete Feedback
6 | Frontend Customer Web Application | General | Static Pages | Home, Services, Subservices | Display Homepage, Services and Subservices | Harshil
|  |  |  | About, FAQ, Contact Us | Display About, FAQ, Contact Us
|  | Customer Registration/Login |  | Registration, Login | Registration and Login Form
Forgot Password
|  | Cart Management | Cart | Manage Cart(Request Services) | Add/Remove Cart Items
Update Cart Items
|  | Customer Account | Profile | Manage Profile | Display/Update Profile
Change Password
|  | Feedback Management | Feedback | Send Feedback to Service Provider/Admin | Add/Remove Feedback
Update Feedback
|  | Order Management | Orders |  | Display Orders
7 | Backend Admin and Customer Management | Services | Sub Services | Manage Services | ListAllservices | Vrunda
ListSubServices
Add Service
Update Service
Delete Service
|  | Customer Management | Customers | Manage Customer | Add Customer
Update Customer Profile
Login/Registration
|  | Feedback Management |  | Manage Feedback | Add Feedback
view Feedback
|  | Provider Management | Service Provider | Manage service Provider | Add Provider
Delete Provider
|  | cart Management |  | Manage cart | Add Service To Cart
|  |  |  | order Management | Place Order
view Order